## Changes and Improvements Log
NFCC EMERGENCY RESPONSE VEHICLES FRAMEWORK AGREEMENT (DS478-24) - CHANGE LOG - 3RD JULY 2026
Ref. | Date added | Title/Topic | Description of Change/Improvement | Relevant to Framework Documents List the documents that are affected by the proposed change/improvement | Raised By | Agreed Action | Person Responsible for making the Change / Improvement | Status | Version Number of Updated Document | Variation Agreement Required? | Variation Reference | Amended Document Published on NFCC ERV Website? | Date of Completion / Closure
1 | 2026-04-02 | Contract Details Notice | Update the link to the published Contract Details Notice | Part 1 - Framework Background |  | Add in the link and publish new version |  | Complete | 020426 | No - Minor Change | N/A | Yes | 2026-04-02
2 | 2026-04-22 | Guidance and Table Update | • Update the Contracting Authority guidance • Add Requirement Type column into Contracting Authority requirements table in each section • Update numbering • Update the score marking numbers on page 4 • Remove FRSs through the document | Appendix 2a Statement of Requirements Aerial Appliances Appendix 2a Statement of Requirements Pumping Appliances Appendix 2a Statement of Requirements Special Vehicles Appendix 2a Statement of Requirements Vehicle Disposal Appendix 2c Statement of Requirements Non-Technical |  | Update the guidance, add in Requirement Type column, update numbering, update scoring number to 5 and remove FRSs |  | Complete | 220426 | No - Minor Change | N/A | Yes | 2026-04-22
3 | 2026-04-22 | Question Numbering, Formula Update and Assessment Panel | • Update the question numbering to match Appendix 2a - Statement of Requirement Vehicle Disposal • Update the formulas in the summary sheet and disposal tab • Remove assessment panel box | Appendix 1b Assessment matrix for Lot 4 |  | Update the numbering and remove the assessment panel box |  | Complete | 220426 | No - Minor Change | N/A | Yes | 2026-04-22
4 | 2026-04-22 | Tab Update, Formula Update and Assessment Panel | • Update the question numbering to match Appendix 2a - Statement of Requirements Aerials, Pumping Appliance and Special Vehicle • Remove the delivery and organisation tab • Change Customer Support to Technical • Update the summary table • Update the formula in the summary sheet and non-technical • Remove assessment panel box | Appendix 1a Assessment matrix for Lot 1 - 3c |  | Update the numbering, removed the delivery and organisation tab, change the customer support tab to non-technical, update the summary table and remove the assessment panel box |  | Complete | 220426 | No - Minor Change | N/A | Yes | 2026-04-22
5 | 2026-04-22 | Pricing Schedule Numbering | Update the numbering for each vehicle tab to match the relevent Appendix 2a - Statement of Requirements | Appendix 5 Pricing Schedule |  | Update the numbering on each vehicle tab |  | Complete | 220426 | No - Minor Change | N/A | Yes | 2026-04-22
6 | 03/072026 | Further Competition Procedure | • Update pipeline notice information on page 3 • Update PME notice information on page 3 • Update Conducting Further Competition section | Part 2 - Further Competition Procedure |  | Update the information on pipeline notice, PME notice and notice requirements |  | Complete | 030726 | No - Minor Change | N/A | Yes | 2026-07-03
7
8
9
10
11
12
13
14
15
16
17
18
19
20